## Tabelle1
No. | Experimental Stage | when | task | Annotations
1 | Long-term preparation phase | 3 months before experiment | Set study dates and responsibilities (for each study date: Study lead, confederate). Further responsibilities include advertising the study, setting up the questionnaire and online training (learning management system for SCORM files needed), and, where applicable, obtaining ethics approval and preregistration. | Please ensure that one person trained for both the confederate and study lead roles is available as a backup at all times to cover potential absences. In our implementation, online training participation took place on computers in our lab, allowing us to provide technical support and document participation time. This requires preparing the workstations, scheduling lab attendance slots, assigning supervision, and printing the worksheets as part of training preparation.
2 | Long-term preparation phase | 2.5 to 1.5 months before the experiment | Prepare chosen booking system for participants to sign in for the experiment | We used the booking system "dfn schedule" (https://terminplaner.dfn.de). There is a booking list for employees and a second one for leaders.
3 | Long-term preparation phase | 1.5 months before the experiment | Advertise the study | We advertised our study on our department's website, in our university's student newsletter, on the university's central psychology experiment server, in email distribution lists for key university research projects and student WhatsApp groups.
4 | Long-term preparation phase | from now until the start of the experiment | Confirmation Email: Continuously check whether anyone has registered for the experiment; if so, send a confirmation email (see document "email templates").
5 | Long-term preparation phase | 2 weeks before the experiment | Monitoring Participant Registration: Check whether enough participants have registered, otherwise advertise specific dates again where participants are missing.
6 | Final preparation phase | 2 days before the experiment | Ensure that the assigned study lead has the key to the laboratory for the relevant study date.
7 | Final preparation phase | 1 day before the experiment | Check the chosen booking system to see who has registered to participate.
8 | Final preparation phase | 1 day before the experiment | Remind participants of the experiment. To do this, send a group email to each group, using the Bcc function. | All participants are placed in the Bcc field to maintain anonymity.
9 | Final preparation phase | 1 day before the experiment | Participant Overview Table: Create an overview table with email address, date, roles, participant code, IC/CC, t0 video file name, T1 video file name, Limesurvey ID, duration of training participation, email addresses and team number to be pre-filled. | IC = intervention condition; CC = control condition
10 | Final preparation phase | 1 day before the experiment | Decide which group is IC and which is CC and note this in the table
11 | Final preparation phase | 1 hour before the experiment | Digital preparation of individual workstations: are the questionnaire and Zoom desktop shortcuts visible on the desktops? Hints for Zoom: Is the right camera selected in each case? Are role names set as first names in the meeting? | For us, the correct camera was the "integrated camera" in Zoom (an additional camera was used to obtain a separate video recording for the FaceReader analysis)
12 | Final preparation phase | 1 hour before the experiment | Physical preparation of individual workstations: Is each workstation labeled with a name tag (Noah, Bene, etc.) and are the digital role descriptions available on the desktops?
13 | Final preparation phase | 1 hour before the experiment | Physical materials for the study lead: Have the instructions for reading aloud (see document "Instructions for getting in tune with the care context"), the schedule (which participants are expected today?), the document for creating participant codes, and the overview table of participants for conducting the experiment (see row 10) been printed out? It is best to have a printed/digital checklist so that you can tick off the steps during the experiment.
14 | Final preparation phase | 1 hour before the experiment | Only relevant for t1 assessment: For participants who are expected to attend, add up how long they participated in the training. If someone did not participate at all, talk to them again at the end to see if this is correct or if we have overlooked something. | As an incentive, we also offered the opportunity to accumulate course credits for psychology students. Anything over 1 hour of training participation can be counted as a total of 7 participant hours at the end (after all, they also had to put in the effort to do the exercises). If the person did not participate in the training, they will be credited with only 4 test subject hours instead of 7.
15 | Final preparation phase | 10 minutes before the experiment | Zoom Setup and Technical Checks: Start Zoom, open the link on all computers. This will take everyone to the Zoom waiting room, check that the "integrated camera" is set up. Let everyone into the meeting. Then minimize the Zoom meeting on the participants' computers and move it to the bottom right corner so that it is not disturbing the participants. Also change your username to ‘Study Lead’ and use the host tool to give everyone permission to share their screen. Check that the microphone and video are enabled on the participants' computers, but that the computer sound is muted. | We had a desktop shortcut "Meeting Experiment". Computer sound has to be muted since everyone is sitting in the same room.
16 | Final preparation phase | 10 minutes before the experiment | Open the survey and booking system for training times on all computers, open materials on the desktop. Leave the survey as the start screen. Switch on the lights in the lab. | Switching on the light in the room is important for a good model quality in the FaceReader analyses
17 | Experimental phase | as soon as all participants are present | T0 Role Assignment: Depending on how many participants are present, assign roles as follows: Ideally: 5 employees and 1 leader. leader is seated in the leader's place (marked by ‘Role description Kim’ on the table); the confederate takes the seat with role description 'Alexis'. If leader is not present: the study lead takes on the role. If 1 employee is not present: omit Finn's role. If 2 employees are not present: omit Finn's and Marlo's roles. If more than 3, 4 or 5 employees are not present: you do not have enough employees, so the experiment cannot be carried out. Apologize to those present and check with them which of the reserve dates might be suitable. Send an email to those who are absent to see if they are available then. Other case: Someone does not speak German well enough: For employees: Please assign the role of Marlo/Finn (they do not score any points themselves). For leaders: Discuss it (in a friendly and discreet manner) with the leader. Ask him/her if it would be okay for us to ask the group if someone else (ideally with some experience in leading groups) could take on the role of the leader. | Our leader had to have at least a C1 level of German since our experiment was conducted in German.
18 | Experimental phase |  | T1 Attendance Contingencies: What to do if someone does not attend? Top priority: Participants must remain in the training group (IC/CC; employees/leader) from the t0 assessment. Also important: Where possible, employees should play exactly the same role they had in the T0 assessment. However, if, for example, Finn (who does not actually have an agenda item) is present, but Noah (who does have an agenda item) is absent, the original Finn should now play Noah. If leader is present: - leader + at least 3 employees present – everything is fine! - leader + 2 employees present: you play an employee - leader + 1 employee present: A new date must be found. You can ask those currently present about their availability and create a schedule. leader not present - At least 3 employees present: you play the leader - Fewer than three employees present: A new date must be found. You can ask those currently present about their availability and create a schedule.
19 | Experimental phase |  | Participant Check-In and Seating: Ask all arrivals (as discreetly as possible, in an adjoining room if necessary) for the email address they provided. Then create a participant code for each participant and enter it in the printed overview table. Identify whether the scheduled leader is present based on the email address and seat the leader in the leader’s place. Then follow the T0 Role Assignment rules and assign the remaining participants to the available employee roles/seats; if several employee roles are possible, assign them randomly, leaving the confederate’s seat free. In T0, inform participants whether they are an employee or a leader, and note that nothing should be done on the computer without instruction. | Ask as discreetly as possible as email addresses are personal data and should therefore be requested discreetly. In our technical setup, the email address was collected when participants booked their study appointment and served as an identifier linking the booking to the participants who arrived at the experimental laboratory.
20 | Experimental phase |  | First Survey Part: Everyone fills out the first part of the survey, and at the end they signal (by raising their hands) that they are finished; note that the survey must remain open (second part follows after the meeting). | In our study, the questionnaire had two parts: the first assessed sociodemographic information, well-being, skills, and other psychological characteristics; the second, completed after the simulated meeting, used a cued recall method to assess participants’ evaluations of specific meeting situations, including experienced leadership styles and employee silence. Technically, we implemented this as one questionnaire that was paused during the meeting rather than as two separate questionnaires, avoiding repeated and potentially error-prone entry of the participant code.
21 | Experimental phase |  | Read aloud the audio instructions (should be printed out; see document Instructions for getting in tune with the care context)
22 | Experimental phase |  | Instruct participants to read their instructions (see e.g., T0_instruction Noah). These are available as PDF files on the desktop. Some additional documents referred to in the instructions are also available on the desktop.
23 | Experimental phase |  | Digital Meeting Preparation: Shortly before everyone is ready: Start the Zoom meeting recording. Check that the video, microphone and computer audio are turned off on the study lead's computer.
24 | Experimental phase |  | Recording Setup: Open the OBS programme on the computers and start recording on all computers (except the confederate Alexis), check that the correct camera is selected. It is best to do a quick test on each computer to ensure that the recording is saving correctly and can be played back. Then minimize OBS and maximise Zoom on the participants' screens. Check again that the participants' cameras and microphones are on and the computer sound is off. | OBS programme should only be opened now, we had the problem that it could crash otherwise. Other camera than "integrated camera" has to be selected, for us it was "Logi camera".
25 | Experimental phase |  | Meeting Instruction and Monitoring: Instruct participants clearly to present their faces in the camera and to not have their hands in front of the face. During the meeting, constantly check whether everyone's face is clearly visible on camera, otherwise point this out, and also watch out whether the documents perhaps are being shared for too long. Check whether the confederate is writing something in the chat that you, as the study lead, should address to the relevant participant. Signal that the meeting is starting with a clear sound in order to have a clear time marker for the standardized beginning (say ‘Start’). | If participants have their hands covering their faces, this impairs FaceReader's ability to analyze them. In addition, if the relevant document remains open for too long, the section of the face that FaceReader can recognize becomes too small for too long. The confederate supports the study lead by also paying attention to these sources of error (see T0_Instruction Alexis (confederate)).
26 | Experimental phase |  | Post-Meeting Transition and Second Survey Part: When the participants say goodbye in the simulated meeting, this marks the point at which the simulation ends. Signal again that the meeting has ended with a clear sound (gong or by saying “end of meeting”; this is important so that we later know where to stop the recording for all videos during video editing). Announce that the second part of the survey is now coming up, walk past all participants’ computers and stop the OBS and Zoom recordings, open the browser with the survey, and instruct the participants to fill out the survey (this is the second part) again.
27 | Post-experimental phase | immediately after the meeting | Role Exit: Instruct participants to shake off their roles (e.g. say: "So, now you can officially leave the role you had for the experiment. For some, it was certainly exhausting, perhaps even unpleasant. It can be good to shake off the role for a moment, and I would like to suggest that you do so briefly"). Only after T0: Inform participants that the training session is now taking place. It will last a total of 3 hours on our premises. | We only had a limited number of workstations and therefore participants should select when they want to come for training in the booking system. It is best if they enter this information now (ideally with the booking system tab already open), but they will also receive the link to the booking system via email. They could also stop by spontaneously and see if a workstation is available.
28 | Post-experimental phase | immediately after the meeting | After T1: Incentive Distribution: Hand out appropriate certificate, enter the voucher code that was awarded in the list, have participants sign to confirm receipt of the voucher.
29 | Post-experimental phase | immediately after the meeting | After T1: Debriefing and Confidentiality: The study served to evaluate a training course, for which there was an intervention group and a control group; you were in the IC/CC. We evaluate the training by looking at your survey data to see whether certain outcomes have changed. We also look at whether you behaved differently and showed different emotions in the meeting after participating in the training. We are particularly interested in situations in the meeting where you felt compelled to raise concerns, share information or contribute ideas, e.g. in situation X. In situations such as this, we assess whether emotions such as fear were displayed less frequently after participating in the training and whether issues that bothered you were addressed more often. We would also like to inform you that this meeting participant was privy to the meeting agenda and was supposed to steer the meeting somewhat, i.e. she was a confederate. So if you found her behaviour strange, that was her job; she had a few guidelines to follow. So now you are well informed about the content of our study. Please treat this information as confidential, as others participating in the study should not know in advance exactly what we are investigating, otherwise the data will be influenced. Thank you very much for participating!
30 | Post-experimental phase | after participants left the room | Video File Management and Secure Storage: Select a storage location for the OBS videos. Rename the video files from laptops and drag them to the chosen storage location. Scheme for renaming the videos could be: Team number_Appointment number (t0 assessment=1, t1 asessment=2)_Role_participant code_Date (YYYYMMDD); e.g. 1_1_Noah_AnMa07n_20250220. Move the videos from laptops to a USB stick. Move videos from USB stick to group drive set up with high protection requirements. Download the Zoom meeting from the Zoom account in all versions, including the transcripts, to the group drive. Also rename these videos according to the following scheme: Team number_Appointment number (T0=1, T1=2)_Date. Then delete the videos from the Zoom online portal. | The video material constitutes personal data. Therefore, ensure that it is transferred to a secure storage location suitable for this type of video material as soon as possible.
31 | Post-experimental phase | self-selected time point after completion of the experiment | Video Standardization: Open shortcut, select ‘Open File’, select the video, drag the video ‘down’ into the timeline, play the video and wait for the point where the leader says something for the first time. Then separate the previous section from the following one by clicking on the symbol of the two square brackets next to each other, then click on it (click in the middle), delete it using "Delete", then click at the end of the video (you can move the time slider just above and below the actual video), then determine where the meeting ends by waiting until the study lead says something for the first time, then select the square brackets again and remove the latter part. Finally, export the video on to your selected group drive. | We used Shotcut software
32 | Post-experimental phase | self-selected time point after completion of the experiment | After T0: Send an email to the group with information about the booking system and that they should now train every week until their next appointment on XY (see document "email templates").
33 | Post-experimental phase | self-selected time point after completion of the experiment | FaceReader Emotion Coding: FaceReader analysis from an MP4 video 1. Open FaceReader and create a new project. 2. Add the participant using the participant code. 3. Add a new video analysis and select the MP4 file. 4. Start the analysis and check whether the model-quality bar crosses the dashed line. 5. Open File > Settings > Data Export and select the variables that should be included in the export, including model quality if available. 6. Export the results via File > Export > Detailed log > Excel file. 7. Check whether the Excel file contains the frame-wise intensities of all facial expressions and the model-quality values. | We used FaceReader 9.1